## Sheet 1
ID | ParentID | TaskName | StartDate | EndDate | Progress | Dependencies | Priority | Status | Resource | Cost
1 | 0 | Project Alpha | 1.1.2024 | 12.31.2024 | 0 |  | High | In Progress | Team Lead | 1000000
2 | 1 | Initiation | 1.1.2024 | 1.31.2024 | 100 |  | High | Completed | Project Manager | 50000
3 | 2 | Project Charter | 1.1.2024 | 1.15.2024 | 100 |  | High | Completed | Project Manager | 20000
4 | 2 | Stakeholder Analysis | 1.16.2024 | 1.31.2024 | 100 | 3 | Medium | Completed | Business Analyst | 15000
5 | 1 | Planning | 2.1.2024 | 3.31.2024 | 100 | 2 | High | Completed | Project Manager | 100000
6 | 5 | Requirements Gathering | 2.1.2024 | 2.29.2024 | 100 |  | High | Completed | Business Analyst | 30000
7 | 5 | Project Plan Creation | 3.1.2024 | 3.15.2024 | 100 | 6 | High | Completed | Project Manager | 25000
8 | 5 | Resource Allocation | 3.16.2024 | 3.31.2024 | 100 | 7 | Medium | Completed | HR Manager | 20000
9 | 1 | Design | 4.1.2024 | 5.31.2024 | 90 | 5 | High | In Progress | Design Team | 150000
10 | 9 | System Architecture | 4.1.2024 | 4.30.2024 | 100 |  | High | Completed | System Architect | 50000
11 | 9 | Database Design | 4.15.2024 | 5.15.2024 | 100 | 10 | High | Completed | Database Engineer | 40000
12 | 9 | UI/UX Design | 5.1.2024 | 5.31.2024 | 80 | 10 | Medium | In Progress | UI Designer | 60000
13 | 1 | Development | 6.1.2024 | 10.31.2024 | 60 | 9 | High | In Progress | Dev Team | 400000
14 | 13 | Backend Development | 6.1.2024 | 8.31.2024 | 70 |  | High | In Progress | Backend Dev | 150000
15 | 14 | API Development | 6.1.2024 | 7.15.2024 | 100 |  | High | Completed | Backend Dev | 70000
16 | 14 | Database Integration | 7.16.2024 | 8.31.2024 | 50 | 15 | Medium | In Progress | Database Engineer | 80000
17 | 13 | Frontend Development | 7.1.2024 | 9.30.2024 | 60 | 12 | High | In Progress | Frontend Dev | 130000
18 | 17 | UI Implementation | 7.1.2024 | 8.15.2024 | 80 |  | Medium | In Progress | Frontend Dev | 70000
19 | 17 | Client-side Logic | 8.16.2024 | 9.30.2024 | 40 | 18 | High | In Progress | Frontend Dev | 60000
20 | 13 | Integration | 9.1.2024 | 10.31.2024 | 40 | 14,17 | High | In Progress | Integration Specialist | 120000
21 | 20 | API Integration | 9.1.2024 | 9.30.2024 | 70 |  | High | In Progress | Integration Specialist | 50000
22 | 20 | Third-party Services Integration | 10.1.2024 | 10.31.2024 | 10 | 21 | Medium | In Progress | Integration Specialist | 70000
23 | 1 | Testing | 11.1.2024 | 12.15.2024 | 0 | 13 | High | Not Started | QA Team | 120000
24 | 23 | Unit Testing | 11.1.2024 | 11.20.2024 | 0 |  | Medium | Not Started | QA Engineer | 30000
25 | 23 | Integration Testing | 11.21.2024 | 12.5.2024 | 0 | 24 | High | Not Started | QA Lead | 50000
26 | 23 | User Acceptance Testing | 12.6.2024 | 12.15.2024 | 0 | 25 | High | Not Started | QA Team | 40000
27 | 1 | Deployment | 12.16.2024 | 12.31.2024 | 0 | 23 | High | Not Started | DevOps Team | 80000
28 | 27 | Production Environment Setup | 12.16.2024 | 12.20.2024 | 0 |  | High | Not Started | DevOps Engineer | 30000
29 | 27 | Data Migration | 12.21.2024 | 12.25.2024 | 0 | 28 | Medium | Not Started | Database Engineer | 20000
30 | 27 | Go-Live | 12.26.2024 | 12.31.2024 | 0 | 29 | High | Not Started | DevOps Team | 30000
31 | 1 | Project Management | 1.1.2024 | 12.31.2024 | 50 |  | High | In Progress | Project Manager | 100000
32 | 31 | Team Meetings | 1.1.2024 | 12.31.2024 | 50 |  | Medium | In Progress | Project Manager | 40000
33 | 31 | Status Reporting | 1.1.2024 | 12.31.2024 | 50 |  | Medium | In Progress | Project Manager | 30000
34 | 31 | Risk Management | 1.1.2024 | 12.31.2024 | 50 |  | High | In Progress | Risk Manager | 30000