## Лист1
ID | task_name | start_date | end_date | duration | completion | predecessor | region | product_line | sales_target | assigned_team
1 | Annual Sales Strategy Planning | 2024-01-02 | 2024-01-31 | 22 | 100 |  | Global | All |  | Executive
2 | Market Analysis | 2024-01-02 | 2024-01-12 | 9 | 100 |  | Global | All |  | Research
3 | Competitor Benchmarking | 2024-01-08 | 2024-01-17 | 8 | 100 | 101 | Global | All |  | Research
4 | Sales Targets Definition | 2024-01-15 | 2024-01-19 | 5 | 100 | 102 | Global | All |  | Executive
5 | Resource Allocation | 2024-01-22 | 2024-01-26 | 5 | 100 | 103 | Global | All |  | HR
6 | Strategy Presentation to Board | 2024-01-29 | 2024-01-31 | 3 | 100 | 104 | Global | All |  | Executive
7 | Q1 Sales Campaign - North America | 2024-02-01 | 2024-04-30 | 64 | 90 | 1 | North America | Electronics | 5000000 | NA Team
8 | Campaign Planning | 2024-02-01 | 2024-02-14 | 10 | 100 |  | North America | Electronics |  | NA Team
9 | Sales Team Training | 2024-02-15 | 2024-02-29 | 11 | 100 | 201 | North America | Electronics |  | NA Team
10 | Lead Generation | 2024-03-01 | 2024-03-29 | 21 | 95 | 202 | North America | Electronics |  | NA Team
11 | Sales Execution | 2024-03-04 | 2024-04-30 | 42 | 85 | 203 | North America | Electronics |  | NA Team
12 | Q1 Sales Campaign - Europe | 2024-02-01 | 2024-04-30 | 64 | 85 | 1 | Europe | Home Appliances | 4000000 | EU Team
13 | Campaign Planning | 2024-02-01 | 2024-02-14 | 10 | 100 |  | Europe | Home Appliances |  | EU Team
14 | Sales Team Training | 2024-02-15 | 2024-02-29 | 11 | 100 | 301 | Europe | Home Appliances |  | EU Team
15 | Lead Generation | 2024-03-01 | 2024-03-29 | 21 | 90 | 302 | Europe | Home Appliances |  | EU Team
16 | Sales Execution | 2024-03-04 | 2024-04-30 | 42 | 80 | 303 | Europe | Home Appliances |  | EU Team
17 | Q1 Sales Campaign - Asia Pacific | 2024-02-01 | 2024-04-30 | 64 | 80 | 1 | Asia Pacific | Smartphones | 6000000 | APAC Team
18 | Campaign Planning | 2024-02-01 | 2024-02-14 | 10 | 100 |  | Asia Pacific | Smartphones |  | APAC Team
19 | Sales Team Training | 2024-02-15 | 2024-02-29 | 11 | 100 | 401 | Asia Pacific | Smartphones |  | APAC Team
20 | Lead Generation | 2024-03-01 | 2024-03-29 | 21 | 85 | 402 | Asia Pacific | Smartphones |  | APAC Team
21 | Sales Execution | 2024-03-04 | 2024-04-30 | 42 | 75 | 403 | Asia Pacific | Smartphones |  | APAC Team
22 | Q1 Sales Campaign - Latin America | 2024-02-01 | 2024-04-30 | 64 | 75 | 1 | Latin America | Home Appliances | 3000000 | LATAM Team
23 | Campaign Planning | 2024-02-01 | 2024-02-14 | 10 | 100 |  | Latin America | Home Appliances |  | LATAM Team
24 | Sales Team Training | 2024-02-15 | 2024-02-29 | 11 | 100 | 501 | Latin America | Home Appliances |  | LATAM Team
25 | Lead Generation | 2024-03-01 | 2024-03-29 | 21 | 80 | 502 | Latin America | Home Appliances |  | LATAM Team
26 | Sales Execution | 2024-03-04 | 2024-04-30 | 42 | 70 | 503 | Latin America | Home Appliances |  | LATAM Team
27 | New Product Launch - Smart Home Devices | 2024-03-01 | 2024-06-30 | 88 | 60 | 1 | Global | Smart Home | 10000000 | Product Team
28 | Product Development Finalization | 2024-03-01 | 2024-03-29 | 21 | 100 |  | Global | Smart Home |  | R&D Team
29 | Marketing Material Preparation | 2024-03-18 | 2024-04-12 | 20 | 90 | 601 | Global | Smart Home |  | Marketing
30 | Sales Team Product Training | 2024-04-15 | 2024-04-26 | 10 | 80 | 602 | Global | Smart Home |  | Training
31 | Pre-launch Customer Presentations | 2024-04-29 | 2024-05-24 | 20 | 50 | 603 | Global | Smart Home |  | Sales
32 | Official Launch and Sales Start | 2024-05-27 | 2024-06-30 | 25 | 30 | 604 | Global | Smart Home |  | All Teams
33 | Q2 Sales Campaign - North America | 2024-05-01 | 2024-07-31 | 66 | 40 | 2 | North America | Smart Home | 7000000 | NA Team
34 | Campaign Planning | 2024-05-01 | 2024-05-14 | 10 | 100 |  | North America | Smart Home |  | NA Team
35 | Sales Team Training | 2024-05-15 | 2024-05-28 | 10 | 100 | 701 | North America | Smart Home |  | NA Team
36 | Lead Generation | 2024-05-29 | 2024-06-28 | 23 | 50 | 702 | North America | Smart Home |  | NA Team
37 | Sales Execution | 2024-06-03 | 2024-07-31 | 43 | 20 | 703 | North America | Smart Home |  | NA Team
38 | Q2 Sales Campaign - Europe | 2024-05-01 | 2024-07-31 | 66 | 35 | 3 | Europe | Electronics | 5500000 | EU Team
39 | Campaign Planning | 2024-05-01 | 2024-05-14 | 10 | 100 |  | Europe | Electronics |  | EU Team
40 | Sales Team Training | 2024-05-15 | 2024-05-28 | 10 | 100 | 801 | Europe | Electronics |  | EU Team
41 | Lead Generation | 2024-05-29 | 2024-06-28 | 23 | 40 | 802 | Europe | Electronics |  | EU Team
42 | Sales Execution | 2024-06-03 | 2024-07-31 | 43 | 15 | 803 | Europe | Electronics |  | EU Team
43 | Mid-Year Performance Review | 2024-07-01 | 2024-07-19 | 15 | 0 | 2,3,4,5,7,8 | Global | All |  | Executive
44 | Data Compilation and Analysis | 2024-07-01 | 2024-07-10 | 8 | 0 |  | Global | All |  | Analytics
45 | Report Preparation | 2024-07-11 | 2024-07-17 | 5 | 0 | 901 | Global | All |  | Analytics
46 | Presentation to Management | 2024-07-18 | 2024-07-19 | 2 | 0 | 902 | Global | All |  | Executive
47 | Q3-Q4 Strategy Adjustment | 2024-07-22 | 2024-08-09 | 15 | 0 | 9 | Global | All |  | Executive
48 | Strategy Revision | 2024-07-22 | 2024-08-02 | 10 | 0 |  | Global | All |  | Executive
49 | Team Alignment Meetings | 2024-08-05 | 2024-08-09 | 5 | 0 | 1001 | Global | All |  | All Teams
50 | Ongoing Sales Activities | 2024-01-02 | 2024-12-31 | 262 | 50 |  | Global | All | 50000000 | All Teams
51 | Weekly Sales Team Meetings | 2024-01-02 | 2024-12-31 | 262 | 50 |  | Global | All |  | All Teams
52 | Monthly Performance Tracking | 2024-01-02 | 2024-12-31 | 262 | 50 |  | Global | All |  | Analytics
53 | Customer Relationship Management | 2024-01-02 | 2024-12-31 | 262 | 50 |  | Global | All |  | Sales
54 | Quarterly Sales Forecasting | 2024-01-02 | 2024-12-31 | 262 | 50 |  | Global | All |  | Finance