## Sheet 1
ID | parent_id | task_name | start_date | end_date | duration | completion | predecessor | region | product_line | sales_target | assigned_team
1 |  | Global Product Launch 2024 | 1.1.2024 | 12.31.2024 | 366 | 50 |  | Global | All | 10000000 | Executive
2 | 1 | Project Initiation | 1.1.2024 | 1.31.2024 | 31 | 100 |  | Global | All |  | Executive
3 | 2 | Stakeholder Meeting | 1.1.2024 | 1.3.2024 | 3 | 100 |  | Global | All |  | Executive
4 | 2 | Project Charter | 1.4.2024 | 1.10.2024 | 7 | 100 | 3 | Global | All |  | Project Management
5 | 2 | Team Assembly | 1.11.2024 | 1.31.2024 | 21 | 100 | 4 | Global | All |  | HR
6 | 1 | Research & Planning | 2.1.2024 | 3.31.2024 | 60 | 100 | 2 | Global | All |  | Research
7 | 6 | Market Analysis | 2.1.2024 | 2.29.2024 | 29 | 100 |  | Global | All |  | Research
8 | 7 | NA Market Research | 2.1.2024 | 2.15.2024 | 15 | 100 |  | North America | All |  | Research
9 | 7 | EU Market Research | 2.1.2024 | 2.20.2024 | 20 | 100 |  | Europe | All |  | Research
10 | 7 | APAC Market Research | 2.1.2024 | 2.25.2024 | 25 | 100 |  | Asia Pacific | All |  | Research
11 | 7 | LATAM Market Research | 2.1.2024 | 2.29.2024 | 29 | 100 |  | Latin America | All |  | Research
12 | 6 | Competitor Analysis | 3.1.2024 | 3.15.2024 | 15 | 100 | 7 | Global | All |  | Research
13 | 6 | Product Requirements | 3.16.2024 | 3.31.2024 | 16 | 100 | 12 | Global | All |  | Product Management
14 | 1 | Product Development | 4.1.2024 | 9.30.2024 | 183 | 80 | 6 | Global | All |  | Development
15 | 14 | Electronics Line | 4.1.2024 | 8.31.2024 | 153 | 90 |  | Global | Electronics |  | Development
16 | 15 | Smartwatch Development | 4.1.2024 | 6.30.2024 | 91 | 100 |  | Global | Electronics |  | Development
17 | 15 | Smart Home Hub Development | 5.1.2024 | 8.31.2024 | 123 | 80 |  | Global | Electronics |  | Development
18 | 14 | Smartphone Line | 4.1.2024 | 9.30.2024 | 183 | 70 |  | Global | Smartphones |  | Development
19 | 18 | Budget Smartphone | 4.1.2024 | 7.31.2024 | 122 | 100 |  | Global | Smartphones |  | Development
20 | 18 | Flagship Smartphone | 5.1.2024 | 9.30.2024 | 153 | 60 |  | Global | Smartphones |  | Development
21 | 1 | Quality Assurance | 6.1.2024 | 10.31.2024 | 153 | 70 |  | Global | All |  | QA
22 | 21 | Electronics QA | 6.1.2024 | 9.30.2024 | 122 | 80 | 15 | Global | Electronics |  | QA
23 | 21 | Smartphone QA | 7.1.2024 | 10.31.2024 | 123 | 60 | 18 | Global | Smartphones |  | QA
24 | 1 | Marketing Preparation | 7.1.2024 | 11.30.2024 | 153 | 50 |  | Global | All |  | Marketing
25 | 24 | Global Marketing Strategy | 7.1.2024 | 7.31.2024 | 31 | 100 |  | Global | All |  | Marketing
26 | 24 | NA Marketing Campaign | 8.1.2024 | 11.30.2024 | 122 | 60 | 25 | North America | All | 3000000 | Marketing
27 | 24 | EU Marketing Campaign | 8.15.2024 | 11.30.2024 | 108 | 50 | 25 | Europe | All | 2800000 | Marketing
28 | 24 | APAC Marketing Campaign | 9.1.2024 | 11.30.2024 | 91 | 40 | 25 | Asia Pacific | All | 3200000 | Marketing
29 | 24 | LATAM Marketing Campaign | 9.15.2024 | 11.30.2024 | 77 | 30 | 25 | Latin America | All | 2000000 | Marketing
30 | 1 | Sales Preparation | 10.1.2024 | 12.15.2024 | 76 | 30 |  | Global | All |  | Sales
31 | 30 | Sales Strategy Development | 10.1.2024 | 10.31.2024 | 31 | 100 |  | Global | All |  | Sales
32 | 30 | NA Sales Training | 11.1.2024 | 11.30.2024 | 30 | 80 | 31 | North America | All |  | Sales
33 | 30 | EU Sales Training | 11.1.2024 | 11.30.2024 | 30 | 70 | 31 | Europe | All |  | Sales
34 | 30 | APAC Sales Training | 11.15.2024 | 12.15.2024 | 31 | 50 | 31 | Asia Pacific | All |  | Sales
35 | 30 | LATAM Sales Training | 11.15.2024 | 12.15.2024 | 31 | 40 | 31 | Latin America | All |  | Sales
36 | 1 | Product Launch | 12.1.2024 | 12.31.2024 | 31 | 10 | 14,21,24,30 | Global | All |  | All
37 | 36 | NA Product Launch | 12.1.2024 | 12.7.2024 | 7 | 20 |  | North America | All | 1500000 | All
38 | 36 | EU Product Launch | 12.8.2024 | 12.14.2024 | 7 | 10 | 37 | Europe | All | 1400000 | All
39 | 36 | APAC Product Launch | 12.15.2024 | 12.21.2024 | 7 | 5 | 38 | Asia Pacific | All | 1600000 | All
40 | 36 | LATAM Product Launch | 12.22.2024 | 12.31.2024 | 10 | 0 | 39 | Latin America | All | 1000000 | All